## Version Control
Version | Description | Who | When
1 | Submitted for Jeff to Review | Mohamed Mehrz | March-11-2021

## OPR-01
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user, I want to Access the WSP-ECE Features
| Prerequisites: | 1-The user has an IAM Account 2-The user had an Operator Security Role 3-The operator is registered to the program 4-The Operator's application is renewed
Status
| Acceptance Criteria | User Can see registration information User Can see and click on the program features within the Program functional panel |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page loaded |  |  | Pass/Fail/Not Executed | Optional
2 | Click WE Program Button |  | Program overview page loaded with the registration information which are •Application Status •Registration Date •Renewal Deadline •# of Registered Employees (# of Active Employees, if any) •# of Pending Applications (# of Applications requiring Operator) links to additional program features are shown within the Program Functions panel: •Registered Employees •Pending Applications •Monthly Hours Submissions •Monthly Funding Statements

## OPR-02
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user, I want to Access the WSP-ECE Features
| Prerequisites: | 1-The user has an IAM Account 2-The user has an Operator Security Role 3-The operator is NOT registered to the program
Status
| Acceptance Criteria | User Can see Operator Profile info Program Status is Unregistered User is provided with link to register |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page loaded |  |  | Pass/Fail/Not Executed | Optional
2 | Click WE Program Button |  | No Registration info is shown No program feature links are shown A program Status is "Unregistered" A Register button is shown as well as a call-to-action message: “You are not currently registered in the WSP-ECE. Please click on the Register button to complete and submit your application.”

## OPR-03
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user, I want to Access the WSP-ECE Features
| Prerequisites: | 1-The user has an IAM Account 2-The user has an Operator Security Role 3-The operator is registered to the program 4-The Operator's application is within the allowed Renewal Period
Status
| Acceptance Criteria | User Can see registration information User Can see see and click on the renewal button User Can see and click on the program features within the Program functional panel |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page loaded |  |  | Pass/Fail/Not Executed | Optional
2 | Click WE Program Button |  | Program overview page loaded with the registration information which are •Application Status •Registration Date •Renewal Deadline •# of Registered Employees (# of Active Employees, if any) •# of Pending Applications (# of Applications requiring Operator) A Renew Button Is shown An Alert Message is shown “Your renewal date is upcoming. Please click on the Renew button to review and acknowledge the conditions for remaining in the WSP-ECE.” links to additional program features are shown within the Program Functions panel: •Registered Employees •Pending Applications •Monthly Hours Submissions •Monthly Funding Statements

## OPR-04
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user, I want to Access the WSP-ECE Features
| Prerequisites: | 1-The user has an IAM Account 2-The user Does Not Have an Operator Security Role
Status
| Acceptance Criteria | User Can't Access any information |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page Doesn't load |  |  | Pass/Fail/Not Executed | Optional

## OPR-05
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user, I want to Access information about my facilities
| Prerequisites: | 1-The user has an IAM Account 2-The user had an Operator Security Role 3-The operator is registered to the program 4-The Operator's application is renewed
Status
| Acceptance Criteria | User Can see Operator Profile Inforamtion User list of his/her licensed facility/facilities User Can click on the details to see more detailed information about his/her facility |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page loaded Operator Profile Infortmaiton are displayed List of licensed facility/facilities is displayed A "Detail" link is displayed next to each facility |  |  | Pass/Fail/Not Executed | Optional

## OPR-06
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user, I want to register participation in the WSP-ECE
| Prerequisites: | 1-The user has an IAM Account 2-The user has an Operator Security Role 3-The operator is NOT registered to the program
Status
| Acceptance Criteria | The Start Date is set to the date/time the form was submitted. The End Date is set to the next upcoming Renewal Deadline for the program. A copy of the Terms and Conditions are emailed to the User as confirmation of the successful registration |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page loaded |  |  | Pass/Fail/Not Executed | Optional
2 | Click WE Program Button |  | No Registration info is shown No program feature links are shown A program Status is "Unregistered" A Register button is shown as well as a call-to-action message: “You are not currently registered in the WSP-ECE. Please click on the Register button to complete and submit your application.”
3 | Click on Register Button |  | application form is displayed with the following : •The Terms and Conditions for the Operator Registration. •A checkbox to confirm the User’s acceptance of the Terms and Conditions. •A text field for the User to provide their name as part of the confirmation
4 | Check the confirmation checkbox |  | The checkbox is checked
5 | Write your full name |  | Your name is displayed
6 | Click Submit |  | Program Overview page is loaded

## OPR-07
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user, I want to renew my participation in the WSP-ECE
| Prerequisites: | 1-The user has an IAM Account 2-The user has an Operator Security Role 3-The operator is registered to the program 4-The Operator's application is within the allowed Renewal Period
Status
| Acceptance Criteria | User Can see registration information User Can see see and click on the renewal button User Can see and click on the program features within the Program functional panel |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page loaded |  |  | Pass/Fail/Not Executed | Optional
2 | Click WE Program Button |  | Program overview page loaded with the registration information which are •Application Status •Registration Date •Renewal Deadline •# of Registered Employees (# of Active Employees, if any) •# of Pending Applications (# of Applications requiring Operator) A Renew Button Is shown An Alert Message is shown “Your renewal date is upcoming. Please click on the Renew button to review and acknowledge the conditions for remaining in the WSP-ECE.” links to additional program features are shown within the Program Functions panel: •Registered Employees •Pending Applications •Monthly Hours Submissions •Monthly Funding Statements
3 | Click on Renew Button |  | application form is displayed with the following : •The Terms and Conditions for the Operator Registration. •A checkbox to confirm the User’s acceptance of the Terms and Conditions. •A text field for the User to provide their name as part of the confirmation
4 | Check the confirmation checkbox |  | The checkbox is checked
5 | Write your full name |  | Your name is displayed
6 | Click Submit |  | Program Overview page is loaded

## OPR-08
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user, I want to Access the WSP-ECE Features
| Prerequisites: | 1-The user has an IAM Account 2-The user has an Operator Security Role 3-The user has an Educator Role 3-The operator is registered to the program 4-The Operator's application is renewed
Status
| Acceptance Criteria | User Can see Operator Home User Can see Educator Home |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Under User Account there should be two links one for Operator Home and the other one for Educator Home |  |  | Pass/Fail/Not Executed | Optional
2 | Click on Operator Home then Click WE Program Button |  | Program overview page loaded with the registration information which are •Application Status •Registration Date •Renewal Deadline •# of Registered Employees (# of Active Employees, if any) •# of Pending Applications (# of Applications requiring Operator) links to additional program features are shown within the Program Functions panel: •Registered Employees •Pending Applications •Monthly Hours Submissions •Monthly Funding Statements
3 | Click On Educator Home then click on the employer details |  | Operator details page loaded where two pieces of information are displayed •Employment Details •Wage Enhancement Program
Note on C6: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: It has to be tested to know what are the expected result as it is not clear

## OPR-09
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user, I want to review the list of Employees registered in my facility/facilities
| Prerequisites: | 1-The user has an IAM Account 2-The user had an Operator Security Role 3-The operator is registered to the program 4-The Operator's application is renewed
Status
| Acceptance Criteria | •A list of Employees registered to the User’s Organization are displayed and shows: Employee Name, Work Status, First Registration date in the WSP-ECE,A Details link |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page loaded Operator Profile Infortmaiton are displayed List of licensed facility/facilities is displayed A "Detail" link is displayed next to each facility |  |  | Pass/Fail/Not Executed | Optional
2 | Click on Registered Employees link presented in the Program Features panel |  | Registered Employees List Page loaded

## OPR-10
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user,I want to register a new Employee that does not have email address or can’t access the portal for participation in the WSP-ECE
| Prerequisites: | 1-The user has an IAM Account 2-The user had an Operator Security Role 3-The operator is registered to the program 4-The Operator's application is renewed 5-The Educator doesn't have IAM Account 6- The Educator is not participated in the program under this facility
Status
| Acceptance Criteria | •A new Employment Record Profile is created based on the form submission. •All supporting Training and Consent documentation is uploaded and associated to the Employee record. •A new Employee Application is created with a status of Under EECD Review and includes the submitted Educational Training information. |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page loaded Operator Profile Infortmaiton are displayed List of licensed facility/facilities is displayed A "Detail" link is displayed next to each facility |  |  | Pass/Fail/Not Executed | Optional
2 | Click on Registered Employees link presented in the Program Features panel |  | Registered Employees List Page loaded
3 | Click on Add New Employee Button |  | Employee Application Page loaded
4 | Check on the checkbox at the declaration of Employee Portal Access |  | Display message loaded with a link of downloadable PDF to print and let the employee sign , scan
5 | Fill in the application form |  | fileds are filled with the entered information
6 | Upload the related documents |  | uploaded documents appear on the page
7 | Check the Checkbox of the declaration |  | Checkbox is checked
8 | Sign your full name |  | Entered name appear
9 | Click Submit |  | Registered Employee List Page loaded

## OPR-11
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user,I want to register a new Employee that has email address , doesn't have IAM Account and not participated in the program
| Prerequisites: | 1-The user has an IAM Account 2-The user had an Operator Security Role 3-The operator is registered to the program 4-The Operator's application is renewed 5-The Educator has an e-mail address 6-The Educator doesn't have IAM Account 7-The Educator is not participated in the program under this facility
Status
| Acceptance Criteria | •A new Employment Record Profile is created based on the form submission. •All supporting Training and Consent documentation is uploaded and associated to the Employee record. •An IAM account is created •An e-mail with IAM account invitation is sent to the Educator E-mail address •A new Employee Application is created with a status of Under EECD Review and includes the submitted Educational Training information. •An email is sent to the Employee’s email address, directing them to the Operator portal in order to provide Consent for participation in the program |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page loaded Operator Profile Infortmaiton are displayed List of licensed facility/facilities is displayed A "Detail" link is displayed next to each facility |  |  | Pass/Fail/Not Executed | Optional
2 | Click on Registered Employees link presented in the Program Features panel |  | Registered Employees List Page loaded
3 | Click on Add New Employee Button |  | Employee Application Page loaded
4 | Fill in the application form |  | fileds are filled with the entered information
5 | Upload the related documents |  | uploaded documents appear on the page
6 | Check the Checkbox of the declaration |  | Checkbox is checked
7 | Sign your full name |  | Entered name appear
8 | Click Submit |  | Registered Employee List Page loaded

## OPR-12
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user, I want to register an Employee that has IAM account and has employment record for participation in the WSP-ECE
| Prerequisites: | 1-The user has an IAM Account 2-The user had an Operator Security Role 3-The operator is registered to the program 4-The Operator's application is renewed 5-The Educator has an e-mail address 6-The Educator has an IAM Account 7-The Educator is participated in the program under this facility
Status
| Acceptance Criteria | No Information will be updated |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page loaded Operator Profile Infortmaiton are displayed List of licensed facility/facilities is displayed A "Detail" link is displayed next to each facility |  |  | Pass/Fail/Not Executed | Optional
2 | Click on Registered Employees link presented in the Program Features panel |  | Registered Employees List Page loaded
3 | Click on Add New Employee Button |  | Employee Application Page loaded
4 | Fill in the application form |  | fileds are filled with the entered information
5 | Upload the related documents |  | uploaded documents appear on the page
6 | Check the Checkbox of the declaration |  | Checkbox is checked
7 | Sign your full name |  | Entered name appear
8 | Click Submit |  | Registered Employee List Page loaded

## OPR-13
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user,I want to register a new Employee that has email address , IAM account and not participated in the program
| Prerequisites: | 1-The user has an IAM Account 2-The user had an Operator Security Role 3-The operator is registered to the program 4-The Operator's application is renewed 5-The Educator has an e-mail address 6-The Educator has IAM Account 7-The Educator is not participated in the program under this facility
Status
| Acceptance Criteria | •A new Employment Record Profile is created based on the form submission. •All supporting Training and Consent documentation is uploaded and associated to the Employee record. •A new Employee Application is created with a status of Under EECD Review and includes the submitted Educational Training information. •An email is sent to the Employee’s email address, directing them to the Operator portal in order to provide Consent for participation in the program |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page loaded Operator Profile Infortmaiton are displayed List of licensed facility/facilities is displayed A "Detail" link is displayed next to each facility |  |  | Pass/Fail/Not Executed | Optional
2 | Click on Registered Employees link presented in the Program Features panel |  | Registered Employees List Page loaded
3 | Click on Add New Employee Button |  | Employee Application Page loaded
4 | Fill in the application form |  | fileds are filled with the entered information
5 | Upload the related documents |  | uploaded documents appear on the page
6 | Check the Checkbox of the declaration |  | Checkbox is checked
7 | Sign your full name |  | Entered name appear
8 | Click Submit |  | Registered Employee List Page loaded

## OPR-14
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user,I want to register an Employee that his last name and date of birth matches an existing record for participation in the WSP-ECE
| Prerequisites: | 1-The user has an IAM Account 2-The user had an Operator Security Role 3-The operator is registered to the program 4-The Operator's application is renewed 5-The Educator has an e-mail address 6-The Educator has IAM Account 7-The Educator information matches with an existing record
Status
| Acceptance Criteria | Message will be prompted that possible matches were found and to consider reactivating found Employee’s work status No Information will be updated |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page loaded Operator Profile Infortmaiton are displayed List of licensed facility/facilities is displayed A "Detail" link is displayed next to each facility |  |  | Pass/Fail/Not Executed | Optional
2 | Click on Registered Employees link presented in the Program Features panel |  | Registered Employees List Page loaded
3 | Click on Add New Employee Button |  | Employee Application Page loaded
4 | Fill in the application form |  | fileds are filled with the entered information
5 | Upload the related documents |  | uploaded documents appear on the page
6 | Check the Checkbox of the declaration |  | Checkbox is checked
7 | Sign your full name |  | Entered name appear
8 | Click Submit |  | Registered Employee List Page loaded

## OPR-15
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Operator Portal | Creation Date: | 2021-03-11 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a user, I want to review the details of an educator
| Prerequisites: | 1-The user has an IAM Account 2-The user had an Operator Security Role 3-The operator is registered to the program 4-The Operator's application is renewed
Status
| Acceptance Criteria | •Educator's details are displayed |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page loaded Operator Profile Infortmaiton are displayed List of licensed facility/facilities is displayed A "Detail" link is displayed next to each facility |  |  | Pass/Fail/Not Executed | Optional
2 | Click on Registered Employees link presented in the Program Features panel |  | Registered Employees List Page loaded
3 | Click details button for an educator |  | Registered WE Staff Details page loaded

## OPR-16
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Review the details of an educators | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a registered and renewed operator, I want to review the details of educators.
| Prerequisites: | 1-The user has an IAM Account 2-The user had an Operator Security Role 3-The operator is registered to the program 4-The Operator's application is renewed
Status
| Acceptance Criteria | •Educator's details are displayed |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | login with IAM account |  | Operator Profile page loaded Operator Profile Infortmaiton are displayed List of licensed facility/facilities is displayed A "Detail" link is displayed next to each facility |  |  | Pass/Fail/Not Executed | Optional
2 | Click on Registered Employees link presented in the Program Features panel |  | Registered Employees List Page loaded
3 | Click details button for an educator |  | Registered WE Staff Details page loaded

## OPR-17
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Edit Employment Record | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As a registered and renewed operator, I want to review the details of educators.
| Prerequisites: | • The User has navigated to the Employee Details Page • The User has an active Operator Registration • The User clicks on the Edit button in the Employment Record Details panel to access the Edit Employment Record Page
Status
| Acceptance Criteria | Educator’s employment status changed to be Active |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Click on employment Status Dropdown menu |  | Active¦On-Leave¦Inactive appeared to specify the Employee’s current work status |  |  | Pass/Fail/Not Executed | Optional
2 | Choose Active status |  | employment status is Active
3 | Click save button |  | Changes are saved
4 | Employee Details Page |  | Registered WE Staff Details page appears

## OPR-18
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Edit Employment Record | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator, I want to update the educator’s employment status to be On-Leave
| Prerequisites: | • The User has navigated to the Employee Details Page • The User has an active Operator Registration • The User clicks on the Edit button in the Employment Record Details panel to access the Edit Employment Record Page
Status
| Acceptance Criteria | Educator’s employment status changed to be On-Leave |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Click on employment Status Dropdown menu |  | Active¦On-Leave¦Inactive appeared to specify the Employee’s current work status |  |  | Pass/Fail/Not Executed | Optional
2 | Choose On-Leave status |  | employment status is On-Leave
3 | Click save button |  | Changes are saved
4 | Employee Details Page |  | Registered WE Staff Details page appears

## OPR-19
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Edit Employment Record | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator, I want to update the educator’s employment status to be inactive
| Prerequisites: | • The User has navigated to the Employee Details Page • The User has an active Operator Registration • The User clicks on the Edit button in the Employment Record Details panel to access the Edit Employment Record Page
Status
| Acceptance Criteria | Educator’s employment status changed to be inactive |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Click on employment Status Dropdown menu |  | Active¦On-Leave¦Inactive appeared to specify the Employee’s current work status |  |  | Pass/Fail/Not Executed | Optional
2 | Choose inactive status |  | employment status is inactive
3 | Click save button |  | Changes are saved
4 | Employee Details Page |  | Registered WE Staff Details page appears

## OPR-20
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Edit Employment Record | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator, I want to update the educator’s employment date
| Prerequisites: | • The User has navigated to the Employee Details Page • The User has an active Operator Registration • The User clicks on the Edit button in the Employment Record Details panel to access the Edit Employment Record Page
Status
| Acceptance Criteria | The educator’s employment date is updated |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Write the date when the current employment status is to end |  | The end date is written |  |  | Pass/Fail/Not Executed | Optional
2 | Write the date when the new status is to take effect |  | The new date is written
3 | Click save button |  | Changes are saved
4 | Employee Details Page |  | Registered WE Staff Details page appears

## OPR-21
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Edit Employment Record | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator, I want to update the educator’s hourly wage
| Prerequisites: | • The User has navigated to the Employee Details Page • The User has an active Operator Registration • The User clicks on the Edit button in the Employment Record Details panel to access the Edit Employment Record Page
Status
| Acceptance Criteria | The educator’s hourly wage is updated |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Click on Hourly wage text box | - | The box is ready to re-write on it |  |  | Pass/Fail/Not Executed | Optional
2 | write 21.0 | 21.0 hours | 21.0 hours are written in the text box
3 | Click save button |  | Changes are saved
4 | Employee Details Page |  | Registered WE Staff Details page appears

## OPR-22
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Edit Employment Record | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator, I want to update the educator’s hourly wage, make it below 11
| Prerequisites: | • The User has navigated to the Employee Details Page • The User has an active Operator Registration • The User clicks on the Edit button in the Employment Record Details panel to access the Edit Employment Record Page
Status
| Acceptance Criteria | The educator’s hourly wage updated to be below 11 |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Click on Hourly wage text box | - | The box is ready to re-write on it |  |  | Pass/Fail/Not Executed | Optional
2 | write 10.0 | 10.0 hours | 10.0 hours are written in the text box
3 | Click save button |  | Changes are saved
4 | Employee Details Page |  | Registered WE Staff Details page appears

## OPR-23
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Edit Employment Record | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator, I want to update the educator’s work role to make him Operator, Operator/Administrator, Operator/Administrator/Educator, Operator/Educator, Administrator/Educator, Administrator, Educator
| Prerequisites: | • The User has navigated to the Employee Details Page • The User has an active Operator Registration • The User clicks on the Edit button in the Employment Record Details panel to access the Edit Employment Record Page
Status
| Acceptance Criteria | update the educator’s work role |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | from staff roles choose check box Operator | - | educator’s work role is Operator |  |  | Pass/Fail/Not Executed | Optional
2 | from staff roles choose check boxes Operator and Administrator | - | educator’s work role is Operator/Administrator
3 | from staff roles choose check boxes Operator, Administrator and Educator | - | educator’s work role is Operator/Administrator/Educator
4 | from staff roles choose check boxes Operator and Educator | - | educator’s work role is Operator/Educator
5 | from staff roles choose check boxes Administrator and Educator | - | educator’s work role is Administrator/Educator
6 | from staff roles choose check box Administrator | - | educator’s work role is Administrator
7 | from staff roles choose check box Educator | - | educator’s work role is Educator
8 | Click save button |  | Changes are saved
9 | Employee Details Page |  | Registered WE Staff Details page appears

## OPR-24
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Edit Employment Record | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator with more than one licensed facility, I want to update the educator Licenses to work in All facilities
| Prerequisites: | • The User has navigated to the Employee Details Page • The User has an active Operator Registration • The User clicks on the Edit button in the Employment Record Details panel to access the Edit Employment Record Page
Status
| Acceptance Criteria | Update the educator Licenses to work in All facilities |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | From Licence choose All checkbox | - | Educator Licenses is updated to work in All facilities |  |  | Pass/Fail/Not Executed | Optional
2 | Click save button |  | Changes are saved
3 | Employee Details Page |  | Registered WE Staff Details page appears
-
-
-
-

## OPR-25
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Edit Employment Record | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator with more than one licensed facility, I want to update the educator Licenses to work in some of the facilities
| Prerequisites: | • The User has navigated to the Employee Details Page • The User has an active Operator Registration • The User clicks on the Edit button in the Employment Record Details panel to access the Edit Employment Record Page
Status
| Acceptance Criteria | Update the educator Licenses to work in some of the facilities |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | From Licence choose ( YMCA Park ST ASP (504005) ) and ( YMCA Royal RD.ASP (504010) ) checkboxes | - | Educator Licenses is updated to work in ( YMCA Park ST ASP (504005) ) and ( YMCA Royal RD.ASP (504010) ) facilities |  |  | Pass/Fail/Not Executed | Optional
2 | Click save button |  | Changes are saved
3 | Employee Details Page |  | Registered WE Staff Details page appears
-
-
-
-

## OPR-26
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Edit Employment Record | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator with more than one licensed facility, I want to update the educator Licenses to work in one facility.
| Prerequisites: | • The User has navigated to the Employee Details Page • The User has an active Operator Registration • The User clicks on the Edit button in the Employment Record Details panel to access the Edit Employment Record Page
Status
| Acceptance Criteria | Update the educator Licenses to work in one facility |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | From Licence choose ( YMCA Park ST ASP (504005) ) checkbox | - | Educator Licenses is updated to work in ( YMCA Park ST ASP (504005) ) facility |  |  | Pass/Fail/Not Executed | Optional
2 | Click save button |  | Changes are saved
3 | Employee Details Page |  | Registered WE Staff Details page appears
-
-
-
-

## OPR-27
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Edit Employment Record | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator with one licensed facility, I want to update the educator Licenses to not to work in the facility while his Employment status is active.
| Prerequisites: | • The User has navigated to the Employee Details Page • The User has an active Operator Registration • The User clicks on the Edit button in the Employment Record Details panel to access the Edit Employment Record Page
Status
| Acceptance Criteria | Update the educator Licenses to not to work in the facility while his Employment status is active. |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Click on employment Status Dropdown menu |  | Active¦On-Leave¦Inactive appeared to specify the Employee’s current work status |  |  | Pass/Fail/Not Executed | Optional
2 | Choose Active status |  | employment status is Active
3 | From Licence don’t choose any checkbox |  | No facility is selected
4 | Click save button |  | Changes are saved
5 | Employee Details Page |  | Registered WE Staff Details page appears
-
-

## OPR-28
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Upgrade Employee Training | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator, I want to upgrade the Educational training for an educator
| Prerequisites: | • The User has navigated to the Employee Details Page. • The User has an active Operator Registration. • The User clicks on the Upgrade Training button in the Education Training Details panel to access the Upgrade Training Application Page
Status
| Acceptance Criteria | Upgrade the Educational training for an educator |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Click on Document Type Dropdown and select Degree | - | Degree type is chosen |  |  | Pass/Fail/Not Executed | Optional
2 | Click Browse button | - | Opening your computer files to search in it.
3 | Click upload | - | Submit supporting documentation to prove validity of the claim of training.
4 | Click Submit button | - | On Submission of a valid form, a new Upgrade Training Application is created with a status of Under EECD Review and includes the submitted Educational Training information then redirect the the user back to the Employee Details Page.
-
-

## OPR-29
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Pending Applications List | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator, I want to review the list of All Applications created for their organization
| Prerequisites: | • The User has navigated to the Program Overview Page. • The User has an active Operator Registration. • The User clicks on the Pending Applications link presented in the Program Features panel to access the Pending Applications List Page
Status
| Acceptance Criteria | Operator user can review the list of All Applications created for their organization |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Operator clicks on the Pending Applications link presented in the Program Features panel to access the Pending Applications List Page | - | list of All Applications for their organization created appears |  |  | Pass/Fail/Not Executed | Optional
-
-
-
-
-

## OPR-30
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Pending Applications List | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator, I want to review the list of pending Applications created for their organization
| Prerequisites: | • The User has navigated to the Program Overview Page. • The User has an active Operator Registration. • The User clicks on the Pending Applications link presented in the Program Features panel to access the Pending Applications List Page
Status
| Acceptance Criteria | Operator user can review the list of pending Applications created for their organization |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Operator clicks on the Pending Applications link presented in the Program Features panel to access the Pending Applications List Page | - | list of All Applications for their organization created appears |  |  | Pass/Fail/Not Executed | Optional
2 | Click on Historical checkbox to toggle the filter for the list results to show all Applications | - | By default filter shows only Pending Applications
-
-
-
-

## OPR-31
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Pending Applications List | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator, I want to export a list of pending Applications created for their organization
| Prerequisites: | • The User has navigated to the Program Overview Page. • The User has an active Operator Registration. • The User clicks on the Pending Applications link presented in the Program Features panel to access the Pending Applications List Page
Status
| Acceptance Criteria | Operator user can export a list of pending Applications created for their organization |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Operator clicks on the Pending Applications link presented in the Program Features panel to access the Pending Applications List Page | - | list of All Applications for their organization created appears |  |  | Pass/Fail/Not Executed | Optional
2 | Click on Historical checkbox to toggle the filter for the list results to show all Applications | - | By default filter shows only Pending Applications
3 | Click on utility link | - | exporting of the presented list as a generated Excel file (refer to Utility and Report Scenarios).
-
-
-

## OPR-32
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Pending Applications List | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an operator, I want to export a list of All Applications created for their organization
| Prerequisites: | • The User has navigated to the Program Overview Page. • The User has an active Operator Registration. • The User clicks on the Pending Applications link presented in the Program Features panel to access the Pending Applications List Page
Status
| Acceptance Criteria | Operator user can export a list of All Applications created for their organization |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Operator clicks on the Pending Applications link presented in the Program Features panel to access the Pending Applications List Page | - | list of All Applications for their organization created appears |  |  | Pass/Fail/Not Executed | Optional
2 | Click on utility link | - | exporting of the presented list as a generated Excel file (refer to Utility and Report Scenarios).
-
-
-
-

## OPR-33
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Pending Applications List | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an Operator, I want to update details of a Draft application for an educator
| Prerequisites: | • The User has navigated to the Program Overview Page. • The User has an active Operator Registration. • The User clicks on the Pending Applications link presented in the Program Features panel to access the Pending Applications List Page
Status
| Acceptance Criteria | Operator user can update details of a Draft application for an educator. |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Navigate Employee Application Details Page | - | WE Application details appears |  |  | Pass/Fail/Not Executed | Optional
2 | Click on Save as Draft | - | The User redirect back to the Registered Employee List Page.
-
-
-
-

## OPR-34
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Pending Applications List | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an Operator, I want to review details of a pending application for a specific educator
| Prerequisites: | • The User has navigated to the Program Overview Page. • The User has an active Operator Registration. • The User clicks on the Pending Applications link presented in the Program Features panel to access the Pending Applications List Page
Status
| Acceptance Criteria | Operator user can review details of a pending application for a specific educator. |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Navigate Employee Application Details Page | - | WE Application details appears |  |  | Pass/Fail/Not Executed | Optional
2 | Click on Save and submit button | - | details of a pending application for the specified educator appears
-
-
-
-

## OPR-35
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Pending Applications List | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an Operator, I want to upload documents for an application in the “Clarification Requested” Status
| Prerequisites: | • The User has navigated to the Program Overview Page. • The User has an active Operator Registration. • The User clicks on the Pending Applications link presented in the Program Features panel to access the Pending Applications List Page
Status
| Acceptance Criteria | Operator user can upload documents for an application in the “Clarification Requested” Status |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Navigate Employee Application Details Page | - | WE Application details appears |  |  | Pass/Fail/Not Executed | Optional
2 | Click on Withdraw button | - | details of a pending application for the specified educator appears
3 | Click on Document Type Dropdown and select Degree | - | Degree type is chosen
4 | Click Browse button | - | Opening your computer files to search in it.
5 | Click upload | - | Submit supporting documentation to prove validity of the claim of training.
6 | Click Submit button | - | On Submission of a valid form, a new Upgrade Training Application is created with a status of Under EECD Review and includes the submitted Educational Training information then redirect the the user back to the Employee Details Page.
-

## OPR-36
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Pending Applications List | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | 36- As an Operator, I want to delete previously uploaded documents
| Prerequisites: | • The User has navigated to the Program Overview Page. • The User has an active Operator Registration. • The User clicks on the Pending Applications link presented in the Program Features panel to access the Pending Applications List Page
Status
| Acceptance Criteria | Operator user can delete previously uploaded documents |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Navigate Employee Application Details Page | - | WE Application details appears |  |  | Pass/Fail/Not Executed | Optional
2 | Click on (red button X) | - | Remove the file from the list/cancel its upload
-
-
-
-
-

## OPR-37
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Pending Applications List | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an Operator, I want to view Admin information section
| Prerequisites: | • The User has navigated to the Program Overview Page. • The User has an active Operator Registration. • The User clicks on the Pending Applications link presented in the Program Features panel to access the Pending Applications List Page
Status
| Acceptance Criteria | Operator user can view Admin information section |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Navigate Employee Application Details Page | - | WE Application details appears |  |  | Pass/Fail/Not Executed | Optional
2 | Observe Application Status, Last Review Date and Notes | - | Read-only text values of Application Status, Last Review Date and Notes appears.
-
-
-
-
-

## OPR-38
LOGO | Project Name: | Education and Early Childhood Development Wage Support Program | Created by: |  | Reviewed By:
| Module Name: | Pending Applications List | Creation Date: | 2021-03-21 | Review date:
| Release Version: |  | Tester's Name: |  | Test Date:
| User Story | As an Operator, I want to Withdraw an approved application for an Educator
| Prerequisites: | • The User has navigated to the Program Overview Page. • The User has an active Operator Registration. • The User clicks on the Pending Applications link presented in the Program Features panel to access the Pending Applications List Page
Status
| Acceptance Criteria | Operator user can Withdraw an approved application for an Educator |  |  | PASS/FAIL/…
Step # | Step Details | Test Case Data | Expected Result | Post-condition | Actual Result | Status | Tester's Notes
1 | Navigate Employee Application Details Page | - | WE Application details appears |  |  | Pass/Fail/Not Executed | Optional
2 | Click on checkbox | - | User declare the inforamtion is accurate.
| Click on Withdraw button | - | details of a pending application for the specified educator appears
-
-
-
-